## Sheet1
CAR_PP_Review
Project Name: | Car Purchasing Web Application
Project Manager Name: | Sarah Ibrahim
Project Description: | This Platform will host an enormous database of cars enabling the sellers to advertise and market their cars and to help the buyer to search for their desired cars
Reviewed by: | Jannat Saeed
Section | Comment
Project title | Project title is " Car Purchasing Web Application " not " Car Reservation Project"
Purpose of Plan | it's " Car Purchasing Application" instead of " Car rental reservation system"
Purpose of Plan | You can remove the word " secure " from the purpose as security is out of scope
Project Goals & Objective | the first point is not clear enough
Scope Definition | Transaction per second for website is " 500 TPS" not " 500 ms".
Scope Definition | Is the customer say " 500 users" or it's just your assumption?
Risk Assessment | Refer than the Communications plan is discussed at the end of the document
Initial Project Risk Assessment | in the point of " Team size at peak", how did you write " over 15 members" while we are just 6 members
Project Approach | You mentioned than we work with agile scrum approach while we didn't decide yet
Project R&R | what is the " steering committee"
Project R&R | i can't understand " Subject Matter Experts" point
Communications plan | You can also write than we communicate together using a whatsapp group and communicate with the customer using mail and the project manager should be CC-ed in any mail
General | You can add the Test plan and exit criteria to the plan