## GanttChart
[Car Purchase] Project Schedule | [8 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
ITI
| Project Start Date | 2019-04-27 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6
| Project Lead | Sara Ibrahim | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13 | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27
 | time axis 2019-04-22 to 2019-06-02
WBS | TASK | Assigned to | PREDECESSOR | START | END | Estimated DAYS | % DONE | WORK DAYS | time axis 2019-04-22 to 2019-06-02
| Phase One | [6 empty] | -
1.1 | Gathering requirements | All team |  | 2019-04-27 | 2019-05-04 | 7 | 100% | 5
1.1.1 | SIQ Sheet | Jannat |  | 2019-04-27 | 2019-05-02 | 4 | 100% | 4
1.1.2 | SRS Sheet | Bossy |  | 2019-04-28 | 2019-05-03 | 6 | 100% | 6
1.1.3 | Risk management sheet | Sara |  | 2019-04-28 | 2019-05-01 | 4 | 100% | 4
1.1.4 | Issue Sheet | Jannat |  | 2019-04-28 | 2019-05-01 | 4 | 100% | 3
1.1.5 | CM tool | Fatma |  | 2019-04-28 | 2019-05-02 | 5 | 100% | 3
1.1.6 | Project plan document | Hagar |  | 2019-04-28 | 2019-04-28 | 1 | 100% | 1
1.1.7 | Project schedule | Mina |  | 2019-04-30 | 2019-05-25 | 5 | 100% | 5
| Phase Two | [6 empty] | -
2.1 | Design | All team |  | 2019-05-04 | Sat 5/11/19 | 7 | 100% | 6
2.1.1 | HLD in SDD | Mina |  | 2019-05-05 | 2019-05-10 | 3 | 100% | 5
2.1.2 | DFD in SDD | Hagar |  | Sun 5/05/19 | Tue 5/07/19 | 1 | 100% | 3
2.1.3 | Class Diagram in SDD | Jannat & Fatma |  | Thu 5/09/19 | Fri 5/10/19 | 1 | 100% | 2
2.1.4 | Use Case Diagram in SDD | Sara |  | Tue 5/07/19 | Fri 5/10/19 | 2 | 100% | 4
2.1.5 | Sequence Diagram in SDD | Bosy |  | Tue 5/7/19 | Fri 5/10/19 | 2 | 100% | 4
2.1.6 | Updated Project Plan | Hagar |  | Tue 5/7/19 | Fri 5/10/19 | 2 | 100% | 4
2.1.7 | Updated SRS | Bosy |  | 2019-05-05 | 2019-05-06 | 2 | 100% | 2
2.1.8 | Wire frames in SDD | Bosy |  | 2019-05-08 | 2019-05-10 | 1 | 100% | 3
2.1.9 | ERD | Jannat |  | Tue 5/07/19 | Tue 5/07/19 | 1 | 100% | 1
Phase Three
3.1 | Build and development | All team |  | Sat 5/11/19 | Sat 5/18/19 | 5 | 10%
3.1.1 | Develop Back End | Bosy |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.2 | Database Implementation | Bosy |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.3 | Registration form | Hagar |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.4 | About us | Fatma |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.5 | See More | Fatma |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.6 | Edit Profile | Fatma |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.7 | Home Page | Hagar |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.8 | User Page | Hagar |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.9 | Add Users | Hagar |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.10 | Reserved Cars | Hagar |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.11 | Web Headers | Jannat |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 30%
3.1.12 | Updated SRS | Sara & Mina |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 40%
3.1.13 | Updated RTM | Sara & Mina |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
3.1.14 | Updated Project Plan | Hagar |  | Mon 5/13/19 | Fri 5/17/19 | 5 | 0%
| Phase four | [6 empty] | -
4.1 | Testing | [5 empty] | 0% | -
[7 empty] | 0% | -
[7 empty] | 0% | -
[7 empty] | 0% | -
[7 empty] | 0% | -
-
-
| Phase five | [6 empty] | -
5.1 | Maintenance | [5 empty] | 0% | -
[7 empty] | 0% | -
[7 empty] | 0% | -
[7 empty] | 0% | -
[7 empty] | 0% | -
-
-
Note on B7: ====== ID#AAAAC7UcDa8 (2019-05-01 20:37:23) Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: ====== ID#AAAAC7UcDbA (2019-05-01 20:37:23) Task Lead Enter the name of the Task Lead in this column.
Note on D7: ====== ID#AAAAC7UcDbU Predecessor Tasks (2019-05-01 20:37:23) You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: ====== ID#AAAAC7UcDa0 (2019-05-01 20:37:23) Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where end date is the cell reference for the End date of the Predecessor task.
Note on F7: ====== ID#AAAAC7UcDbI End Date (2019-05-01 20:37:23) The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: ====== ID#AAAAC7UcDbM (2019-05-01 20:37:23) Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the Gantt chart references this column.
Note on H7: ====== ID#AAAAC7UcDbQ (2019-05-01 20:37:23) Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: ====== ID#AAAAC7UcDbE (2019-05-01 20:37:23) Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.