## GanttChart
[Car_Purchase] Project Schedule | [9 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
ITI
| Project Start Date | 2019-04-27 |  |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6
| Project Lead | Sara Ibrahim | [7 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13 | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27
 | time axis 2019-04-22 to 2019-06-02
WBS | TASK | Assigned to | PREDECESSOR | Reviewed By | START | END | Estimated DAYS | % DONE | WORK DAYS | time axis 2019-04-22 to 2019-06-02
| Phase One |  |  |  | 2019-04-27 | 2019-05-04 |  |  | 5
1.1 | Gathering requirements | Sara |  |  | 2019-04-27 | 2019-05-04 |  |  | 5
1.1.1 | SIQ Sheet | Jannat |  |  | 2019-04-27 | 2019-05-02 | 2 | 50% | 4
1.1.2 | SRS Sheet | Bossy |  |  | 2019-04-28 | 2019-05-03 |  |  | 5
1.1.3 | Risk management sheet | Sara |  |  | 2019-04-28 | 2019-05-01 |  | 100% | 3
1.1.4 | Issue Sheet | Jannat |  | Sara | 2019-04-28 | 2019-05-01 |  | 100% | 3
1.1.5 | CM tool | Fatma |  |  | 2019-04-28 | 2019-05-02 |  | 100% | 4
1.1.6 | Project plan document | Hagar |  |  | 2019-04-28 | 2019-04-28 |  | 100% | 0
1.1.7 | Project schedule | Mina |  | Hagar | 2019-04-30 | 2019-05-25 |  | 50% | 19
| Phase Two | [7 empty] | -
2.1 | Design |  |  |  | 2019-05-04 | 2019-05-11 |  | 0% | 5
2.1.1 | HLD | Mina |  |  | 2019-05-05 |  |  | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
| Phase Three | [7 empty] | -
3.1 | Build and development | [6 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
| Phase four | [7 empty] | -
4.1 | Testing | [6 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
-
-
| Phase five | [7 empty] | -
5.1 | Maintenance | [6 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
[8 empty] | 0% | -
-
-
Note on B7: ====== ID#AAAAC7UcDa8 (2019-05-01 20:37:23) Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: ====== ID#AAAAC7UcDbA (2019-05-01 20:37:23) Task Lead Enter the name of the Task Lead in this column.
Note on D7: ====== ID#AAAAC7UcDbU Predecessor Tasks (2019-05-01 20:37:23) You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on F7: ====== ID#AAAAC7UcDa0 (2019-05-01 20:37:23) Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: ====== ID#AAAAC7UcDbI End Date (2019-05-01 20:37:23) The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H7: ====== ID#AAAAC7UcDbM (2019-05-01 20:37:23) Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: ====== ID#AAAAC7UcDbQ (2019-05-01 20:37:23) Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J7: ====== ID#AAAAC7UcDbE (2019-05-01 20:37:23) Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.