## Sheet1
CAR_PPReview
Project Name: | Car Purchasing Web Application
Project Manager Name: | Sarah Ibrahim
Project Description: | This Platform will host an enormous database of cars enabling the sellers to advertise and market their cars and to help the buyer to search for their desired cars
Reviewed by: | Jannat Saeed
ID | Comment
CAR_Risk_01 | I think the probability of this risk is 3 not 1
CAR_Risk_02 | I think the probability of this risk is 4 not 1
CAR_Risk_04 | I think the probability of this risk is 1 and severity is 4 not vice versa
CAR_Risk_08 | I think the probability of this risk is 1 and severity is 3 not vice versa
Extra risks can be added | 1. Daily standup meeting that held after the lectures cannot be done with the same duration and efficiency in Ramadan days 2. Unawareness of the all team about any tasks in the next phases 3. Any team member can not use the CM tool 4. Any team member doesn't agree to any decision 5. Any conflict occurs between the project manager and any team member 6. Any team member refuse to participate in the project 7. Exams and presentation may be held in the same week/day besides the required deliverables