## Sheet1
CAR_Design Document_PR
Project Name: | Car Purchasing Web Application
Project Manager Name: | Sarah Ibrahim
Project Description: | This Platform will host an enormous database of cars enabling the sellers to advertise and market their cars and to help the buyer to search for their desired cars
Reviewed by: | Jannat Saeed
ID | Comment | Document Author | Reviewed by | Status
CAR_SDD_01 | In DFD design document diagram I can't understand why there is add,delete ,view and change car status came out from login function. | Hager | Sara | open
CAR_SDD_02 | The guest actor or unregistered user does not exist in DFD diagram. | Hager | Sara | open
CAR_SDD_03 | The last paragraph in DFD description not clear I don't understand the context . | Hager | Sara | open
CAR_SDD_04 | The design of DFD not organized. | Hager | Sara | open
CAR_SDD_05 | In Car_Wireframe_01, it's better to make price in a drop list with 2 options, from high to low and from low to high | Bosy | Jannat | Closed
CAR_SDD_06 | In Car_Wireframe_04, there's a wrong error message appears beside the address field | Bosy | Jannat | Closed
CAR_SDD_07 | In Car_Wireframe_13, unregistered user cannot reach the reserved cars page | Bosy | Jannat | Closed
CAR_SDD_08 | In HLD, the login and sign up functionalities found in arrowed shape instead of rectangle shape | Mina | Jannat | Closed
CAR_SDD_09 | In HLD, the unregistered user cannot see more details about each car | Mina | Jannat | Closed
CAR_SDD_10 | In HLD, the user cannot reserve any car before login | Mina | Jannat | Closed
CAR_SDD_11 | In ERD, in section 6.3 under car entity there are some missing attributes | Jannat | Mina | Closed
CAR_SDD_12 | In ERD, the admin entity has just two attributes | Jannat | Mina | Closed
CAR_SDD_13 | In Use Case diagram there is no comment | Sara | Bosy | Closed
CAR_SDD_14 | In Sequence diagram there is no comment. | Bosy | Fatma | Closed
CAR_SDD_15 | In Class Diagram, we can put section 3.3.1 & 3.3.2 can be merged in one section | Jannat & Fatma | Mina | Closed
CAR_SDD_16 | In Class Diagram, there is no direct line between admin and car manager | Jannat & Fatma | Mina | Closed