## Issue Log
Issue Log
Project Name: | Car Purchasing Web Application
Project Manager: | Sarah Ibrahim
Project Description: | This Platform will host an enormous database of cars enabling the sellers to advertise and market their cars and to help the buyer to search for their desired cars
ID | Issue | Severity | Issue Type | type | Status | Date | Action Plan/Status
Car_QIssue_01 | The version IDs in the revision history table in the beginning of each document don't match the IDs on the CM tool | High |  | Technical | Closed | 2019-04-05 | we just depend on the version IDs on the CM tool
Car_QIssue_02 | There is no meaning to find a requirement sheet and a SRS document and both have the same information | Medium |  | Technical | Closed | 2019-04-05 | The SRS document is removed and now we are just depend on the requirement sheet because the RTM IDs depend on this sheet | Budget | Critical | Open
Car_QIssue_03 | The team does not has the required qualifications to deliver the project and the PM does not require any trainings | Critical |  | Resource | Closed | 2019-04-05 | We asked Eng. Marwan to help us. Each and every design is revised by him this week. | Resource | High | Pending
Car_QIssue_04 | The CIL need to be updated | Medium |  | Technical | Closed | 2019-04-05 | The CIL is restructed and divided in folders and subfolders, and the new structure is now on the CM tool | Schedule | Medium | Closed
Car_QIssue_05 | The NFRs are not clear enough and not testable | High |  | Technical | Open | 2019-04-05 | we asked the customer to clarify more in SIQ, but it still confusing us so we decide to postpone it to the weekly meeting to understand more | Technical | Low | No longer relevant
Car_QIssue_06 | The schedule doesn't has enough details about the starting and ending date | Medium |  | Schedule | Closed | 2019-04-05 | The schedule is updated with the required data
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## Issue-Risk Definitions
Overall Impact | Guidelines
Critical | Risk is required to be escalated to Senior Management, with mitigation options if possible
High | Management item to be monitored by, Project Manager and Senior Management
Medium | Risk for Project Managers to monitor- doesn't require escalation
Low | Risk to track for awareness and monitor if it needs escalation
Severity | Guidelines
4 | Could drive impact to Deployment Date
3 | Could drive impact to intermediate milestone, which could impact deployment date
2 | Could drive impact to tasks and may impact an intermediate milestone
1 | Could drive impact to the project milestone that could easily be absorbed by the project (no Go-Live Item)
Probability | Guidelines
4 | >90% Likelihood of occurrence
3 | 60-89% Likelihood of occurrence
1 | 40-59% Likelihood of occurrence
1 | <39% Likelihood of occurrence
Status | Guidelines
Open | Issue is being monitored/tracked
No longer relevant | Issue/Risk has been investigated and is of no/little concern
Closed | Issue/Risk is closed
Issue Type | Guidelines
Project Management | Addressed and managed by the Project Manager
Infrastructure | Related to hardware, network or enterprise systems
Testing | Related to testing (i.e. Performance testing, User testing, etc)
Training | Related to process or system training
Development | Related to software design, development and system testing
Business | Related to business processes or procedures
Requirements | Related to business or system requirements
etc | Add description