## Sheet1
CAR_RACI
Project Name: | Car Purchasing Web Application
Project Manager Name: | Sara Ibrahim
Project Description: | This Platform will host an enormous database of cars enabling the sellers to advertise and market their cars and to help the buyer to search for their desired cars
Task | Jannat | Mina | Hagar | Fatma | Bosy | Sara
Phase One
Project Plan | I | I | R | I | I | I
Project Plan Review | R | I | I | I | I | I
Schedule | I | R | C | I | I | I
Schedule Review | I | I | I | R | I | I
Risk Sheet | C | I | I | I | I | R
Risk Sheet Review | R | I | I | I | I | I
Issue sheet | R | I | I | I | I | C
Issue sheet Review | I | I | I | I | I | R
SIQ | C | R | I | I | I | I
SIQ Review | I | I | I | I | I | R
SRS | I | I | I | I | R | C
SRS Review | I | R | I | I | I | I
RTM | R | I | I | I | I | I
RTM Review | I | I | I | I | I | R
WBS | I | C | R | I | I | I
WBS Review | I | I | I | I | R | I
CM Plan | I | I | I | R | I | I
CM Plan Review | I | I | I | I | I | R
CM tool configuration | I | I | I | R | I | I
CM Training | I | I | I | R | I | I
Phase Two
HLD in SDD | I | R | I | I | I | I
HLD Review | R | I | I | I | I | I
DFD in SDD | I | I | R | I | I | I
DFD Review | I | I | I | I | I | R
UML Class Diagram in SDD | R | I | I | C | I | I
UML Class Diagram Review | I | R | I | I | I | I
UML Sequence in SDD | I | I | I | I | R | I
UML Sequence Review | I | I | I | R | I | I
UML Use Case in SDD | I | I | I | I | I | R
UML Use Case Review | I | I | I | I | R | I
ERD Diagram | R | I | I | I | I | I
ERD Diagram Review | I | R | I | I | I | I
Wireframe in SDD | I | I | I | I | R | I
Wireframe review | R | I | I | I | I | I
Updated Project Plan | I | I | R | I | I | I
Updated Project Plan Review | I | I | I | R | I | I
Updated SRS | I | I | I | I | R | I
Updated SRS Review | I | C | I | I | I | R
Updated RACI sheet | I | I | I | I | I | R
Updated Schedule sheet | I | I | I | I | I | R
Phase Three
Develop back end | I | I | I | I | R | I
Database Implementation | I | I | I | I | R | I
Registration Form | I | I | R | I | I | I
About Us | I | I | I | R | I | I
See More | I | I | I | R | I | I
Edit Profile | I | I | I | R | I | I
Home Page | I | I | R | I | I | I
User Page | I | I | R | I | I | I
Add Users | I | I | R | I | I | I
Reserved Cars | I | I | R | I | I | I
Web Headers | R | I | I | I | I | I
Add Cars | R | I | I | I | I | I
Updated SRS | I | C | I | I | I | R
Updated SRS PR | R | I | I | I | I | I
Updated RTM | I | R | I | I | I | C
Updated Project Plan | I | I | R | I | I | I
Updated Design Document | C | I | I | I | I | R
Updated RTM PR | R | I | C | I | I | I
Car_known_bugs | R | I | I | I | I | I
Car_WF_RTM_PR | I | R | I | I | I | I