## Issue Log
Issue Log
Project Name: | Car Purchasing Web Application
Project Manager: | Sarah Ibrahim
Project Description: | This Platform will host an enormous database of cars enabling the sellers to advertise and market their cars and to help the buyer to search for their desired cars
ID | Issue | Severity | Issue Type | Status | Action Plan/Status
CAR_Issue_01 | One of our team members was on Vacation, so he couldn’t attend most the preparations and that’s affected on our progress. | Medium | Schedule | Closed
CAR_Issue_02 | Most of our teams members have no experience enough in development especially in the back-end , so we have a gap in numbers of developers | Critical | Technical | Open |  | Budget | Critical | Open
CAR_Issue_03 | The first two days we were on a holiday, so we started to work late because of the lack of communication among the team | Medium | Schedule | No longer relevant |  | Schedule | Medium | Closed
CAR_Issue_04 | All the team are beginners in CM | Low | Technical | Closed | The member who is responsible of the CM document communicated with our CM instructor and try to understand more and help us to work easily with the tool | Technical | Low | No longer relevant
CAR_Issue_05 | We can't find any appropriate free tools for project management | Low | Technical | Closed | We decided to work on Microsoft office
CAR_Issue_06 | The team is not fully dedicated to the project due to daily lectures | High | Schedule | Open | We decided to work in breaks and after lectures daily
CAR_Issue_07 | The team faced a problem with the CM tool, that the confirmed naming convention used by the team was CAR_XXX_V00 and it cause alot of duplication. This problem is due to lack of awareness of CM | High | Technical | Open | We decided to change the naming convension CAR_XXX
CAR_Issue_08 | One of our team members has a problem with the CM tool and she can not commit any changes | Medium | Technical | Open | Any one of the team commit her changes

## Risk Log
Risk Log
Project Name: | Car Purchasing Web Application
Project Manager Name: | Sarah Ibrahim
Project Description: | This Platform will host an enormous database of cars enabling the sellers to advertise and market their cars and to help the buyer to search for their desired cars
ID | Risk | Severity | Probability | Weight | Overall Impact | Risk Type | Status | Plan | Mitigation Plan
CAR_Risk_01 | During Ramadan month the working hours will be decreased and that's may be affected our performance and progress. | 4 | 1 | 4 | Low | Schedule | Open | Mitigate | Working extra hours during night instead of the day. | Open
CAR_Risk_02 | Our team members consists of a lot of testers and few developers and that's can lead to not meet deadline and be behind schedule. | 3 | 1 | 3 | Medium | Development | Open | Mitigate | Exchange roles between team members and involve all team in development tasks. | Closed
CAR_Risk_03 | Members of our teams may have another commitment to attend training and leave our team in the middle of the project | 4 | 2 | 8 | High | Schedule | Open | Mitigate | If that happened we are going to divide the work of the absent member through the team. | No longer relevant
CAR_Risk_04 | Job fair may be occur during this project and that's can lead to make the team distracted and can't perform the given tasks | 4 | 1 | 4 | Critical | Schedule | Open | Mitigate | Make study plan and time management to be ready at any time.
CAR_Risk_05 | The website may be not secured | 2 | 2 | 4 |  | Development | Open | Accept
CAR_Risk_06 | Sudden disconnection in network while the team working in the same workspace. | 2 | 1 | 2 |  | Schedule | Open | Mitigate | Open mobile data 3G or 4G
CAR_Risk_07 | Conflict between team members can happened | 2 | 2 | 4 |  | Resources | Open | Transfer | Project Manager will solve this problem
CAR_Risk_08 | Bosy is the only developer in back end, if she is absent it is going to be critical problem for the rest of the team members. | 3 | 1 | 3 |  | Resources | Open | Transfer | Bosy Shafaay it's her responsibility to solve this problem.
CAR_Risk_09 | The team can make wrong estimations for features. | 3 | 2 | 6 |  | Schedule | Open | Mitigate | Make buffer days to help us for estimation
CAR_Risk_10 | Daily standup meeting that held after the lectures cannot be done with the same duration and efficiency in Ramadan days | 2 | 3 | 6 |  | Schedule | Open | Mitigate | Daily standup meeting can be held in breaks time or through social media applications
CAR_Risk_11 | Unawareness of the all team about any tasks in the next phases | 2 | 2 | 4 |  | Schedule | Open | Accept
CAR_Risk_12 | Any team member can not use the CM tool | 3 | 3 | 9 |  | Technical | Open | Mitigate | Provide training for using CM tool.
CAR_Risk_13 | Any team member doesn't agree to any decision | 3 | 3 | 9 |  | Resources | Open | Mitigate | Make voting for this decision or let the project manager to decide.
CAR_Risk_14 | Any conflict occurs between the project manager and any team member | 2 | 2 | 4 |  | Resources | Open | Mitigate | Knowing the root cause of the problem and try to make decisions and solve it
CAR_Risk_15 | Any team member refuse to participate in the project | 2 | 1 | 2 |  | Resources | Open | Transfer | Project Manager will solve this problem
CAR_Risk_16 | Exams and presentation may be held in the same week/day besides the required deliverables | 2 | 3 | 6 |  | Schedule | Open | Accept

## Issue-Risk Definitions
Overall Impact | Guidelines
Critical | Risk is required to be escalated to Senior Management, with mitigation options if possible
High | Management item to be monitored by, Project Manager and Senior Management
Medium | Risk for Project Managers to monitor- doesn't require escalation
Low | Risk to track for awareness and monitor if it needs escalation
Severity | Guidelines
4 | Could drive impact to Deployment Date
3 | Could drive impact to intermediate milestone, which could impact deployment date
2 | Could drive impact to tasks and may impact an intermediate milestone
1 | Could drive impact to the project milestone that could easily be absorbed by the project (no Go-Live Item)
Probability | Guidelines
4 | >90% Likelihood of occurrence
3 | 60-89% Likelihood of occurrence
2 | 40-59% Likelihood of occurrence
1 | <39% Likelihood of occurrence
Status | Guidelines
Open | Issue is being monitored/tracked
No longer relevant | Issue/Risk has been investigated and is of no/little concern
Closed | Issue/Risk is closed
Issue Type | Guidelines
Project Management | Addressed and managed by the Project Manager
Infrastructure | Related to hardware, network or enterprise systems
Testing | Related to testing (i.e. Performance testing, User testing, etc)
Training | Related to process or system training
Development | Related to software design, development and system testing
Business | Related to business processes or procedures
Requirements | Related to business or system requirements
etc | Add description